First give me an 80 day build plan then the architecture diagram plus schema outline and service boundaries

## 80-day build plan

This plan assumes:

- 30 hrs/week during build

- one vertical only: home-service businesses

- one primary workflow: inbound lead → qualification → booking → follow-up → estimate

- no custom integrations in MVP beyond Twilio, Vapi, Stripe, Supabase, email/SMS

- you are optimizing for first paying customers, not breadth

The sequencing matters. You should build in the order that reduces product risk first, then operational risk, then polish.

### Phase 0: Days 1–4 — product constraints and technical foundation

Goal: lock the product shape so you do not drift into platform-building.

Build:

- mono-repo setup

- environments: local, staging, prod

- CI/CD

- TypeScript strict mode

- linting, formatting, test harness

- secrets management

- base Next.js app

- base backend service

- Supabase project and initial database

- Sentry and PostHog wired in

- Stripe test account and billing skeleton

- vendor abstraction interfaces for:

  - telephony

  - model provider

  - vector/retrieval

  - notifications

Decisions to finalize:

- supported service businesses for MVP: pick one narrow wedge first, such as HVAC or plumbing

- quote style: estimate range only

- booking style: offer available windows, not exact technician promises

- AI voice scope: intake and confirmation only, not full sales conversation

- human review path: mandatory for low-confidence runs

Deliverables:

- working deploy pipeline

- “hello world” tenant-authenticated dashboard

- initial schema migrated

- audit/event logging working end-to-end

Success criteria:

- one-click deploy to staging

- all events and errors visible

- no architectural ambiguity remains

### Phase 1: Days 5–12 — tenant model, auth, state layer, admin shell

Goal: stand up the product shell and data model before AI complexity.

Build:

- Supabase auth

- tenant/account model

- row-level security

- user roles: owner, dispatcher, admin

- core CRUD pages:

  - leads

  - jobs

  - technicians

  - service areas

  - settings

- initial audit log view

- prompt/config storage tables

- API auth middleware

- webhook verification framework

Deliverables:

- accounts and users can sign in

- tenant-isolated CRUD for basic entities

- audit events visible in UI

Success criteria:

- two test tenants cannot access each other’s data

- basic back-office app is usable without AI

### Phase 2: Days 13–22 — inbound lead intake MVP

Goal: prove that an incoming phone lead can become structured, useful business data.

Build:

- Twilio phone number setup

- inbound webhook handling

- Vapi call entry integration

- call session record creation

- transcript ingest pipeline

- extraction pipeline for:

  - caller name

  - phone number

  - address

  - service type

  - urgency

  - preferred time window

- schema validation for extracted fields

- confidence scoring

- fallback path for incomplete extraction

- missed-call detection and SMS callback workflow

UI:

- call detail page

- transcript view

- extracted fields review/edit screen

- lead creation timeline

Deliverables:

- inbound call produces:

  - call record

  - transcript

  - structured intake summary

  - lead record

- missed calls trigger auto text response

Success criteria:

- at least 80% of test calls produce usable lead records with minimal correction

- every extraction result is inspectable and editable

### Phase 3: Days 23–30 — workflow engine and durable orchestration

Goal: move from “events happen” to “business workflows are controlled.”

Build:

- Temporal workflows for:

  - inbound lead intake

  - missed-call follow-up

  - booking confirmation

  - reminder scheduling

  - post-job review request

- workflow state table

- workflow step audit viewer

- retry/backoff policies

- dead-letter / failure queue

- manual retry / resume tooling

Deliverables:

- all important flows are executed through durable workflows

- failures are recoverable without direct DB edits

Success criteria:

- intentionally kill a worker mid-workflow and recover cleanly

- no duplicate notifications after retries

### Phase 4: Days 31–40 — owner-facing automation and follow-ups

Goal: ship the first sticky value that customers immediately feel.

Build:

- SMS confirmation flow

- reminder flow

- post-job review request flow

- business hours rules

- opt-out handling

- notification templating system

- email backup notifications

- lead and job status transitions

- simple dashboard metrics:

  - new leads

  - booked jobs

  - pending confirmations

  - follow-up sent count

Deliverables:

- complete lead-to-confirmation loop

- post-job engagement automation

Success criteria:

- system can process a lead and send the correct follow-ups without human intervention

- notification failures are observable and retryable

### Phase 5: Days 41–52 — scheduling engine

Goal: convert intake into real operational value.

Build:

- technician model

- skill tags

- service area mapping

- availability model

- working hours and blackout windows

- duration heuristics by service type

- buffer/travel logic

- scheduler service

- slot recommendation API

- manual override UI

- booking lock / conflict prevention

Important constraint:
do not build route optimization.
Do not build “optimal fleet dispatch.”
Build simple, reliable scheduling.

Scheduling output should return:

- feasible windows

- assigned technician candidates

- explanation metadata

- confidence

Deliverables:

- system can suggest available service windows

- user can approve or override

- booking confirmation messages are sent only from validated schedule results

Success criteria:

- test set of scheduling cases passes with no double-booking

- deterministic scheduler beats manual spreadsheet scheduling in speed

### Phase 6: Days 53–61 — pricing estimator

Goal: provide high-value quoting support without taking pricing liability you cannot handle.

Build:

- service type taxonomy

- account-specific pricing rules

- base/min/max estimate ranges

- surcharges

- after-hours modifiers

- estimate explanation templates

- quote audit log

- account-level controls:

  - no estimate

  - rough range only

  - internal estimate only

- guardrails:

  - never commit exact price unless explicitly enabled

  - never estimate unsupported service types

  - escalate on low confidence

AI usage here:

- summarize estimate in plain language

- explain factors

- suggest follow-up questions

- never compute authoritative numbers on its own

Deliverables:

- estimate generation endpoint

- UI for maintaining pricing rules

- customer-safe wording for ranges

Success criteria:

- estimate outputs are explainable and rule-backed

- quote policy can be disabled per account or service type

### Phase 7: Days 62–69 — retrieval memory and business knowledge layer

Goal: make the system business-specific without hardcoding every tenant nuance.

Build:

- knowledge base upload

- chunking pipeline

- embeddings generation

- retrieval service

- metadata filters:

  - tenant

  - service type

  - city/zip

  - doc type

  - version

- retrieval citations in audit logs

- admin UI for:

  - upload docs

  - disable stale docs

  - inspect chunks

Use retrieval for:

- FAQs

- service coverage

- objection handling

- SOPs

- internal notes

- price-policy explanations

Do not use retrieval for:

- core state

- scheduling truth

- billing truth

- technician availability

Deliverables:

- tenant knowledge base searchable in AI workflows

- retrieval evidence stored with model runs

Success criteria:

- retrieval consistently pulls the correct tenant context

- no cross-tenant leakage in test scenarios

### Phase 8: Days 70–75 — evaluation, observability, and hardening

Goal: make production survivable.

Build:

- gold test dataset

- offline eval pipeline for:

  - extraction accuracy

  - classification accuracy

  - scheduling correctness

  - quote policy compliance

- online metrics:

  - cost per workflow

  - extraction correction rate

  - manual override rate

  - booking conversion

  - notification failure rate

- prompt versioning UI

- model run explorer

- incident alerts

- daily cost summary

- weekly quality report

Deliverables:

- nightly evaluation job

- visible quality regression detection

- visible cost drift detection

Success criteria:

- you can detect broken prompts, broken retrieval, and broken workflows before customers tell you

- every customer-facing AI action is traceable

### Phase 9: Days 76–80 — beta launch package

Goal: ship something a real business can use and pay for.

Build:

- onboarding wizard

- default prompt/config templates for one vertical

- first-run demo account

- billing activation

- usage metering

- plan enforcement

- admin support panel

- beta docs

- basic terms/privacy pages

- backup/export tools

Operational work:

- onboard 2–5 beta customers manually

- review 20–30 real calls

- tune prompts

- remove obvious friction

- lock scope after beta feedback

Deliverables:

- first paying beta customers

- production checklist complete

- support runbook complete

Success criteria:

- one business can operate on it daily

- you can maintain it without heroics

## Recommended weekly focus split across the 80 days

Given your time budget, this is the rough allocation I would use:

- 45% core product engineering

- 20% AI workflow/evals/prompting

- 15% UI/admin tooling

- 10% infra/observability

- 10% customer discovery and beta onboarding

If you let AI workflow tinkering exceed core product engineering, you will waste the build.

## What not to build in the first 80 days

Do not build:

- route optimization

- deep CRM integrations

- multilingual support

- multi-branch franchise support

- full autonomous quoting

- autonomous technician dispatch

- analytics-heavy reporting suite

- generic “AI agent builder”

- mobile app

- custom workflow editor

- marketplace/app ecosystem

Those are all distraction traps.